## Sheet1
3 developers
Manager-tech expert/PO- domain expert or story writing expert | Sprint 0 | 5days/10 days-- 2 week | login functionality- | agile story--given when then |  | Title
| Sprint 1 | Search functionality | login form--5 days--3 days |  |  | Discription
| Sprint 2 | cart fecility | success/failure |  |  | AC:
| Sprint 3 |  | reset password
| Sprint 4 |  | Register |  |  | DOD- Definition of done
Sprint 5
| Sprint 6 |  | serach for food |  |  | Backlog | social media ligin
| Sprint 7 |  | serach for merchant
Sprint 8
Sprint 9
Sprint 10
| Sprint 11 |  |  | EPICs--login functinality
| Sprint 12 |  |  | Search functionality
cart fecility
payment
feedbach/notification
| story points | who will do this?
login form | 2 | rohit
success/failure | 2 | sai
reset password | 3 | rithika
Register | 3 | revanth
week 1--5 days |  |  | day? | who are involved
7 stages in sprint
1 | Sprint backlog refinement | Login functinality | prior week | manager,PO,client | no developers are involved in this
2 | grooming | assign story points- how much time is needed to complete the task--Estimation-fibbonacci series(1,2,3,5,8(2 week)..) | 1st day-Monday | all of you with client
3 | Planning | to decide who will own the task or contact | Monday | manager,PO with developers
4 | daily srum | daily meetings-- for 30 min to discuss on blockers | tue to fri | all with client
5 | dry run |  | on 4th day-Thursday | all with client
6 | sprint demo | final code delivary | on 5th day-Friday | all with client
7 | Retrospective | How the sprint went?? Feedback to all |  | all | no client in this meeting